## Yuyan Zhang
Project 12 - Your Project Name
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup environment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
3 | Yuyan Zhang | 9 | 8 | 1 | 0 - set up environment and platform: slack, github,pivotal tracker; install virtualbox,Ubuntu,python,Django 1 - attend group meeting,discuss the features and tools for our projects. 2-complete the quality assurance plan part of : textbook<<Software Engineering>> self-studying, including chapter 2,5,9, 25,26,27.learned about quality metrics, and the process of software testing.Then finished the SQAP part on sppp | 1 | 1 | 7 |  |  | 1 |  |  | 5
4 | Yuyan Zhang | 8.5 | 7 | 1.5 | 0-join the group meeting, discuss the detials for first iteration, including(code commit criteria, risk management, architecture) 1-keep learning python, Django （mainly learn syntex from tutorials or youtube ） 2-finished three user sotries on pivotaltracker(@ mention, emoticons, grouping) | 1.5 | 6 | 1 | [5 empty] | 5
5 | Yuyan zhang | 18 | 14 | 4 | 0-start the front end design, and learn all tools for it including Bootstrap, Javascript, jQuery,CSS 2-join the weekly meeting to prepare for the iteration 1 presentation 3- implement two bootstrap components :the scroll bar and drop down list 4-practice for the first presentation | 6 | 4 | 4 | 4 |  |  |  |  | 6
6 | Yuyan Zhang | 2 | 0 | 2 | 0-group meeting for 2nd iteration goals | 2 | [7 empty] | 8
7 | Yuyan Zhang | 13 | 9 | 4 | 0-began the mobile and pc version UI design 1- practiced the github on virtual machine 2-joined the group meeting on Saturday and extra front-end meeting on Tuesday | 8 | 1 | 4 | [5 empty] | 8
8 | Yuyan Zhang | 30 | 26 | 4 | 1-finished the functions of mobile and pc version UI by using bootstrap, CSS, jQuery and javascript 2-learned PyUnit and Selenium webdriver 3-conducted all functional testing cases for 2nd iteration 4-joined the weekly meeting and extra meeting 5-prepared for 2nd iteration presentation and practiced for it | 4 | 5 | 13 | 3 | 5
9 | yuyan zhang | 3 | 1 | 2 | 0-weekly meeitng for 3 iteration 1-finished 2nd iteration summary | 2 | 1
10 | Yuyan zhang | 11.5 | 9 | 2.5 | 0-weekly meeting 1-finished the emoji function , uplaod file function and create room function in UI 2-finished the weekly meeting report | 2.5 | 8 | 1 | [5 empty] | 7
11 | Yuyan zhang | 12 | 10 | 2 | 0-weekly meeting 1-Created the new functonal test cases(emoticons test case, upload file test case, search file test cases and user online status test case) | 2 | 10
12 | Yuyan zhang | 11 | 10 | 1 | 1-prepared to the final presentation (meeting and ppt) 2- Final presentaion 3-finished all ducuments and summary | 6 | 3 | 2

## William Wilson
Project 12 - Your Project Name
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
3 | William Wilson | 12 | 10.5 | 1.5 | 0 - learned tools and setup environments: - learned github, installed git on computer, and setup github respository for team - signed up for pivital tracker and invited team members - installed python in virtual box 3 - Contributed to SPPP document 5 - attended group meeting - setup meeting for team on google hangouts - completed meeting minutes | 5 |  |  | 3 |  | 4 |  | 0 - learn tools and setup environments: - learn python 1 - Contribute to SPPP document - Create User Stories 5 - attended group meeting | 8
4 | William Wilson | 5 | 3.5 | 1.5 | 0 - setup git repository on virtual machine 5 - Participated in meetings and discussions on Slack | 3.5
5 | William Wilson | 15 | 13.5 | 1.5 | 0 - learned how Django models work and how the Django RESTful API works 1 - Created user story and git branch for Django RESTful API endpoints 3 - Worked on RESTful API endpoints for Django models. 5 - Participated in meetins and discussions in Slack. | 13 | 0.5 |  |  | 1.5 |  |  | 0 - lean how Django models work and how the Django RESTful API works. Learn about NodeJS and SocketIO 3 - Create messagedata Django RESTful API endpoint. 5 - Participate in meetings and discussions on Slack.
6 | William Wilson | 15 | 12.5 | 3.5 | 0 - leaned how Django models work and how the Django RESTful API works. Learned about NodeJS and SocketIO 1 - Created user story and git branch for messagedata RESTful API endpoint. 3 - Created messagedata Django RESTful API endpoint. This endpoint allows all of the data associated with a message (user data and room data) to be available at one endpoint. 5 - Participated in meetings and discussions on Slack. | 7.5 | 0.5 |  | 4 | 4 |  |  | 0 - lean how NodeJS and SocketIO work 3 - develop socketIO functions so that they send data in the json format
7 | William Wilson | 6 | 4.5 | 1.5 | 0 - leaned how Django models work and how the Django RESTful API works. Learned about NodeJS and SocketIO 3 - Continued to develop RESTful API endpoint for messagedata. 5 - Participated in meetings and discussions on Slack. | 2 |  |  | 3 |  | 1 |  | 0 - lean how namespaces work 3 - develop separate groups using namespaces
8 | William Wilson | 7 | 5.5 | 1.5 | 0 - leaned how the Django RESTful API works. Learned about NodeJS and SocketIO 3 - worked on using namespaces to create separate chat rooms 5 - Helped teammates to understand how to create branches and push them to the repo. Participated in meetings and discussions on Slack. | 1 |  |  | 3 |  | 3 |  | 0 - lean how namespaces work. namespaces versus channels 3 - develop separate groups using namespaces
9 | William Wilson | 11 | 9.5 | 1.5 | 0 - learned about socket.io namespaces 3 - Developed separate chat rooms using namespaces. 5 - Participated in meetings and discussions on Slack. | 4 |  |  | 5 |  | 2 |  | 0 - lean how NodeJS and SocketIO work 3 - develop a way to create socket.io namespaces dynamically
10 | William Wilson | 10 | 9 | 1 | 0 - learned about socket.io namespaces 3 - Developed a technique to create socket.io namespaces dynamically. Switched to CentOS VM. 5 - Participated in meetings and discussions on Slack. | 3 |  |  | 5 |  | 2 |  | 0 - lean how NodeJS and SocketIO work 3 - create socket.io namespace names using room names
11 | William Wilson | 12 | 11 | 1 | 0 - learned about socket.io namespaces 3 - Developed a technique to create socket.io namespace names by pulling room names from the database. 5 - Participated in meetings and discussions on Slack. | 5 |  |  | 5 |  | 2 |  | 0 - lean how NodeJS and SocketIO work 3 - develop technique to track users to rooms.
12 | William Wilson | 8 | 11 | 1 | 0 - learned about many to many django relationships 3 - Developed user-room model in database. This model will track the relationship between users and rooms. It is an alternative to using many-to-many Django fields. 5 - Participated in meetings and discussions on Slack. | 1 |  |  | 5 |  | 2 |  | 0 - lean how NodeJS and SocketIO work 3 - user-room model api endpoint, and search function
13 | William Wilson | 9 | 11 | 1 | 0 - learned about many to many django relationships 3 - Created API endpoint for user-room table. I spent most of my time this week debugging my CentOS operating system. I had to completely reload it onto a new virtual machine. I worked on developing the search funtion. 5 - Participated in meetings and discussions on Slack. | 1 |  |  | 6 |  | 2 |  | 0 - lean how NodeJS and SocketIO work 3 - search function 5 - project presentation
14 | William Wilson | 9 | 11 | 1 | 0 - learned about many to many django relationships 3 - Worked on search function. This was front end and back end work. Worked on the project presentation. 5 - Participated in meetings and discussions on Slack. | 1 |  |  | 6 |  | 2 |  | 0 - lean how NodeJS and SocketIO work 3 - develop socketIO functions so that they send data in the json format

## Xinzhu Xu
week# | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
3 | Xinzhu Xu | 5.5 | 3 | 2.5 | 0 - Setting up development VMs, virtual environments, Git and Django;Setting up project tools (slack, pivotaltracker, github, etc.) 2- Research about framework and programming language, start to use VM 5- participate in group meeting, starting draft of SPPP | 1 | 2.5 | 2.5 | 0 | 0 | 2.5 |  | 0- set up required environment 1- self-study python and django 2- group meeting 3- discuss with group members about the requirement analysis | 10
4 | Xinzhu Xu | 12 | 10.5 | 1.5 | 0 - learned tools and setup environments: - learned github, installed git on computer, go through github tutorial - signed up for pivital tracker and wrote user stories for our project. - installed python, django, django-rest framework in virtual box 3 - Contributed to SPPP document 5 - attended group meeting - ask questions from Oscar | 3.5
5 | Xinzhu Xu | 13 | 10.5 | 2.5 | 0 - go through django online tutorial and django rest-framework tutorial 1- Created user story on pivotal tracker and continue be familiar with django-rest-framework. 3 - Worked on RESTful API endpoints for Django models. 5. attend the meeting and ask questions on slack. | 10 | 0.5 |  | 1 | 1.5 |  |  | 0 - learn how Django models work and how the Django RESTful API works. Learn about NodeJS and SocketIO 3 - Create messagedata Django RESTful API endpoint. 5 - Participate in meetings and discussions on Slack.
6 | Xinzhu Xu | 16 | 14 | 2 | 0 - continue go through django-rest-framework tutorial, learned Socket IO 1- create user story, contribute to git branch for messagedata RESTful API endpoint. 5 - Participated in meetings and discussions on Slack. | 10 | 3 |  |  | 1 | 2 |  | 0 - learn how Django models work and how the Django RESTful API works. Learn about NodeJS and SocketIO 3 - Create messagedata Django RESTful API endpoint and ask Bill about the relationship between MVC architecture 5 - Participate in meetings and discussions on Slack.
7 | Xinzhu Xu | 7 | 5 | 2 | 0 - leaned how Django models work and how the Django RESTful API works. Learned about NodeJS and SocketIO 3 - Continued to develop RESTful API endpoint for messagedata. 5 - Participated in meetings and discussions on Slack. | 4 |  |  | 2 | 1 | 3 |  | 0 - learn how Django models work and how the Django RESTful API works. Learn about NodeJS and SocketIO 3 - develop separate groups using namespace
8 | Xinzhu Xu | 6 | 4.5 | 1.5 | 0 - leaned how the Django RESTful API works. Learned about NodeJS and SocketIO 3 - worked on urls.py files to create endpoints to retrieve data 5 - Participated in meetings and discussions on Slack. Help teammate to connect to Internet using centos VM | 4 |  |  | 0.5 |  | 1.5 |  | 0 - lean how namespaces work. namespaces versus channels 3 - develop separate groups using namespaces
9 | Xinzhu Xu | 11 | 9.5 | 1.5 | 0 - learned about socket.io namespaces 3 - Developed separate chat rooms using namespaces. 5 - Participated in meetings and writing meeting minutes and discussions on Slack. | 5 |  |  | 3 |  | 1.5 |  | 0 - learn how Django models work and how the Django RESTful API works. Learn about NodeJS and SocketIO 3 - Create 5 - Participate in meetings and discussions on Slack.
10 | Xinzhu Xu | 10 | 8 | 2 | 0 - learned about socket.io namespaces 3 - Switched our project to CentOS VM. 5 - Participated in meetings and discussions on Slack. | 4 |  |  | 2 |  | 2 |  | 0 - learn how NodeJS and SocketIO work 3 - develop a way to create socket.io namespaces dynamicall
11 | Xinzhu Xu | 13 | 10 | 3 | 0 - learned about socket.io namespaces 3 - Developed a technique to create socket.io namespace names by pulling room names from the database. 5 - Participated in meetings and discussions on Slack. | 5 |  |  | 5 |  | 3 |  | 0 - learn how NodeJS and SocketIO work 3 - develop technique to track users to rooms
12 | Xinzhu Xu | 12 | 11 | 1 | 0 - learned about many to many , many to a django models relationships , learn django cook book. 3 - Conrtibute to user-room model in database. Set emoji branch in github and learning how to use emoji plugin in django. 5 - Participated in meetings and discussions on Slack. | 7 |  |  | 3 |  | 1 |  | 0 - learn how NodeJS and SocketIO work 3 - user-room model api endpoint, and read search function.
13 | Xinzhu Xu | 10 | 9 | 1 | 0 - learned about many to many django relationships go through the documentation about search and filter part 3 - Contribute to created API endpoint for user-room table. Worked on search and filter function in django. 5 - Participated in meetings and discussions on Slack. | 3 |  |  | 4 |  | 2 |  | 0 - learn how Django models work and how the Django RESTful API works. Learn about NodeJS and SocketIO 3 - start work on search and filter function 5 - Participate in meetings and discussions on Slack.
14 | Xinzhu Xu | 9 | 7 | 2 | 0 - learned about many to many django relationships 3 - Worked on search function but it didn't work. This was front end and back end work. Worked on the project presentation. 5 - Participated in meetings and discussions on Slack. | 4 |  | 1 |  |  | 2 |  | 0 - learn how Django models work and how the Django RESTful API works. Learn about NodeJS and SocketIO 3 - complete search and filter function 5 - Participate in meetings and discussions on Slack.

## Shishuang Shu
1
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
3 | Shishuang Shu | 10 | 9 | 1.5 | 0-Setup environment and platform for this project: Virtual Box, Ubuntu System, install python and Django,set up python virtualenvironment, Sublime Text2, -Set up git and connect my account to the group project account, slack, etc. 1-requirement anaysis: as the requirement leader, talk with professor about the basic requirement of this tool and get a background and outline. -communicate with our whole group, bring professor's feedback and discuss in details of the requirement, classifying those requirement into functional requirements, non-functional requirements and so on. -Keep in touch with professor, bring new ideas. 2-learn python, Django. research for the knowledge of the framework and web development. 3-Do research and write SPPP. 5-attend group meeting.discuss in details about the first iteration and the basic technique we will use in the first few weeks. | 1.5 | 2 | 4 | 1.5 |  | 1 |  | -Learning Django Framewwork -Reanalysis the requirement. -Design architecture. -make plans for first iteration. | 10
4 | Shishuang Shu | 10.5 | 9 | 1.5 | 0-keep learning Django, python about the models. 1-more deeply analyse the requirement of this tool. Write at least three user storys and acceptance text. Decide the priority of each user storys and make sure which function should be realize in the first iteration. 2-Research about some templates of virtual chatting room and learn the basic policy of them. 3-Try to have a basic draft of user interface. 5-attend the group meeting and discuss about the principal of this communication tool. | 4 | 2 | 1 | 0.5 |  | 1.5 |  | -Learn how to design user interface -Decide what function that should be realized first. -Learn Django especially in templates and models. | 9
5 | Shishuang Shu | 10 | 8.5 | 1.5 | 0-learning Bootstrap and jquery, javascript and make the preparation for design UI 1-According to the priority of each user story, making decisions on the user story to achieve in the first iteration. 2-Start to design UI. 3-Use Bootstrap to design the UI, implemented the basic functions that will be achieved in the first iteration. 4-Test the UI in different browsers. 5-Having group meeting and set up the models for this tool. | 3 | 0.5 | 2 | 2 | 0.5 | 1.5 |  |  | 9
6 | Shishuang Shu | 11 | 8.5 | 2.5 | 0-Learn and use the Bootstrap to develop responsive useriterface. Correct several misatake in layout and scroll area. 1-discuss with other team members to do the requirement analysis and make some changes according to the feedback from the first iteration. 2-writing code and review code to design the UI. 3-Implement with jQuery and JavaScript to achive the functon of sending messages. 5-discuss with team members and show them the UI effect and get advice from them and then edit it again. | 2 | 1 | 4 | 1.5 | 0 | 2.5 | 0 |  | 8
7 | Shishuang Shu | 10 | 8 | 2 | 0-start to learn the bootstrap about how to use the reponsive function and try to make similar ones 1-requirement analysis and decide to make monbile UI 2-design the mobile UI 3-writing code for the mobile UI 4-functional testing. 5-communicate with team member and make decision for the features about to achieve next | 1 | 2 | 2 | 2 | 1 | 2 |  |  | 8
8 | Shishuang Shu | 9 | 8 | 1 | 1-finish the function of mobile userinterface. 2-design to change the header in each room and responsive to the room that the user is in. 3-using jQuery and JavaScript 4-learn how to use selenium and make plan for testing. 5-talk with backend team and learn about their progress.Prepare for the presentation for the iteration 2. | 0 | 1 | 2 | 2 | 2 | 2
9 | Shishuang Shu | 10.5 | 9 | 1.5 | 0-continue to learn how to use bootstrap to make modal for some features. 1-discuss with others who use our tool and ask their opinion and then change some of our requirement 2-frontend work 3-frontend work 4-functional testing 5-communicate with our group member and solve the problem of the layout of some modal | 1 | 2 | 2 | 2 | 2 | 1.5
10 | Shishuang Shu | 9 | 7 | 2 | 1-delete some user stories which are improper and change some priority 2-design mobile version and change some display and layout. 3-frontend part to change "search" bar place and hide. and some other change of the UI 4-unit testing 5-talk with our group memeber and discuss to delete some user stories for the future work | 0 | 1 | 2 | 2 | 2 | 2
11 | Shishuang Shu | 10 | 8 | 2 | 1-from the user stories left to achieve, decided to achieve file uploading, emoji.create new rooms ,etc. 2-design the upload file windows modal, and the way to display. design where to put emoji. 3-implement the features of emoji, upload files, create new rooms 4-testing: unit testing 5-meeting with team discussing the goal for the third iteration and summary for the last two iteration. | 0 | 1 | 2 | 2 | 2 | 2 | 0 | finish the rest of the chosen user stories and implement with user management
12 | Shishuang Shu | 9 | 8 | 1 | 1-according to the score of user stories, choose to achieve some important user stories. 2-frontend design for the emoji and create rooms 3-implemented the new features and implemented with team one. 4-testing the create new rooms features and some other UI functional testing 5-communicate with the team and discuss the final features that we are planing to achive | 0 | 1 | 2 | 2 | 2 | 2 | 0 | prepare for the final presentation next week
13 | Shishuang Shu | 7 | 6 | 1 | 1-summary the requirement analysis for final presentation 3-implemented the final features 4-final testing 5-Communicate with the whole team and discuss about the final presentation | 0 | 1 | 0 | 3 | 2 | 1 | 0 | end

## Oscar Ingham
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
3 | Oscar Ingham | 7 | 5 | 2 | 0 - Setting up development VMs, virtual environments, Git and Django; Setting up project tools (slack, pivotaltracker, github, etc.) 1 - Researched existing communication software to identify potential features 2 - Researched design strategies for real-time chat software; Learned more about Django 5 - Attended group meetings, established strategy with rest of team, began first-draft of SPPP | 2 | 1 | 1 | 0 | 0 | 3 | 0 | 0 - Help rest of team set up environment 1 - Complete list of requirements for first iteration 2 - Design database schema, decide on API and JS framework 3 - Set up basic API framework in Django 4 - Begin writing test suite for API end-points in first iteration 5 - Group meetings | 8
4 | Oscar Ingham | 8 | 6.5 | 1.5 | 0 - Finished setup of development environment and other tools 1 - Continued discussions on features and prioritization of set for first iteration 2 - Continued research into open-source Django based chat applications and general design strategies for real-time chat 5 - Attended group meetings, took meeting minutes, added three user stories to Pivotal Tracker | 1 | 1 | 4 | 0 | 0 | 2 | 0 | 0 - Help rest of team set up environment 1 - Finalize list of requirements for first iteration 2 - Design Django models for first iteration; choose framework for real-time communication 3 - Begin implementation of first iteration 4 - Start writing test suite 5 - Group meetings | 8
5 | Oscar Ingham | 9 | 7.5 | 1.5 | 1 - Finalized requirements for first iteration in pivotal tracker 2 - Finished Django models and added Django rest framework 3 - Completed working SocketIO/Node example 4 - Tested all features manually 5 - Regular Group meetings | 0 | 0.5 | 0.5 | 6 | 0.5 | 1.5 | 0 | 0 - Think about deployment of first iteration on AWS 1 - Prioritize features for second iteration 2 - Split tasks into groups 3 - Complete front-end 4 - Test first iteration 5 - Group meetings
6 | Oscar Ingham | 11 | 9 | 2 | 0 - Deployment of iteration one to AWS cloud; discussion with team members about git 1 - Plan user stories for second iteration 2 - Designate working groups into front and back end; assign features 3 - Finish bootstrap UI and ensure 4 - Manually ensured that all features are working 5 - 2 Group Meetings | 2 | 0.5 | 0.5 | 5 | 1 | 2 | 0 | 1 - Finalize features for second iteration 2 - Work with both groups individually on seprate technology stacks 3 - Add multi-room capability 4 - Write test suite for second iteration 5 - Group meetings
7 | Oscar Ingham | 7 | 6 | 1 | 0 - Research SocketIO namespacing 1 - Discuss features 3 - Work on global namespacing 5 - Group meetings | 1.5 | 1 | 0.5 | 3 | 0 | 1 |  | 1 - Plan iteration 2 2 - Global namespace design 3 - Work on user/room global namespace 5 - Group meetings
8 | Oscar Ingham | 9.5 | 8 | 1.5 | 0 - Researched transition to CentOS 1 - Collateed feedback from first presentation; finalized set of features for iteration 2 2 - Researched global messaging and set individual meetings with front and back end 3 - Began implementation of global namespace 5 - Regular group meetings | 2 | 0.5 | 1.5 | 3 | 0 | 1 |  | 0 - Finalize CentOS transition 2 - Finalize design for global namespacing 3 - Continue working on global room/user messages 4 - Write unit tests 5 - Group meetings; train team on new VM
9 | Oscar Ingham | 9 | 7.5 | 1.5 | 0 - NodeJS research 2 - SocketIO namespace design 3 - Finalized new VM, 5 - Group meetings | 2 | 0 | 1.5 | 4 | 0 | 1.5 |  | 3 - Help with responsive templates 4 - Unit and functional tests 5 - Group meetings
10 | Oscar Ingham | 9 | 7.5 | 1.5 | 0 - Researched bootstrap 2 - Worked more on global namespacing design 3 - Helped with responsive template implementation 4 - Helped with selenium tests 5 - Group meetings | 0.5 | 0 | 1.5 | 3 | 1 | 1.5 |  | 0 - Research Node/SocketIO 2 - Global namespace design 3 - Global namespace implementation 4 - Unit tests 5 - Prep for iteration 2 presentation
11 | Oscar Ingham | 8 | 6.5 | 1.5 | 1 - Finalized requirements for final iteration 2 - Plan user model integration 3 - Begin transition back to Ubuntu, worked on global namespaces, file uploads 4 - Unit tests 5 - Group meetings | 0.5 | 1 | 2 | 3 | 0 | 1.5 |  | 0 - Reseach NodeJS/SocketIO 2 - Work on user integration 3 - Help with emoticons and global namespace featuers 4- Unit tests 5 - Group meetings
12 | Oscar Ingham | 13 | 11.5 | 1.5 | 2 - Worked with Samer to integrate all projects 3 - Implemented all global namespace features, polished emoticons 4 - Finished unit tests 5 - Group meetings | 0.5 | 0 | 4 | 6 | 1 | 1.5 |  | 0 - Prepare for final presentation 3 - Finish all features, deploy to Samer's VM 5 - Group meetings
13 | Oscar Ingham | 11.5 | 10 | 1.5 | 0 - Prepare for final presentation 3 - Finishing touches 5 - Group meetings | 2 | 0 | 0 | 8 | 0 | 1.5 |  | Done!